## Feature Matrix
OM0RX-xLog feature comparison
As of 16 October 2026. OM0RX-xLog states distinguish source implementation, installed/package acceptance and live hardware/service proof. RUMlogNG and QLog entries are limited to the verified sources listed on the Sources sheet.
Implemented or source complete | 34 | Active, partial or outstanding | 9
Feature | OM0RX-xLog | RUMlogNG | QLog
Logbook — local/offline authority | Installed / accepted — local SQLite remains usable offline with local create, edit, delete and search. | Documented — unlimited local logs and QSOs on macOS. | Documented — local SQLite backend on Linux and Windows.
QSO entry — simple and full modes | Source complete — shared canonical draft supports compact Simple and responsive Full editors; packaged acceptance exists for the installed baseline, later radio-owner changes remain source-only. | Documented — normal logging plus a separate specialized contest logger. | Documented — general-purpose QSO logging; customizable interface.
QSO editing — open, edit and delete | Source complete — pointer or keyboard row activation opens the revision-fenced canonical editor; modeled and arbitrary ADIF fields can be added, edited, cleared or deliberately preserved, while the existing safe delete/undo owner remains authoritative. Packaged interaction acceptance remains. | Documented — log editing, searches, queries and import/export workflows. | Documented — log management and custom QSO filters; arbitrary-field editor breadth was not established in the reviewed README.
QSO data quality findings | Source complete for read-only core, exact-contact route and Details UI — QSODataQuality inspects one retained revision using existing validation, supplied dated CTY comparison at QSO date, retained power provenance and exact-context conflict alternatives (5d11996; 5/5 Swift). Stored/manual overrides stay authoritative. Dates retain source/observation/detection roles rather than field origin. Findings supply qualitative impacts only, no correction or award/confirmation/sync delta. Native/package/copied-log/live acceptance, full coverage and corrections remain open. 862e444 adds logbook_data_quality scoped to exact contact/generation/revision, optional primary-key retained conflict, canonical snapshot/current CTY owner with version/date unknown and duplicate review not performed. Main/Logbook only; no corrections/writes/provider refresh/award/sync delta. Swift route 2/2, combined 3/3, Rust auth 1/1, frontend 7/7 and tsc pass; initial route-test compile defects fixed before commit. c4b1602 adds exact-contact read-only Logbook Details findings with explicit Read findings and context retirement. Root 35/35 plus isolated detached 6/6 pass; agent build/tsc/browser geometry pass. No correction/provider refresh/native/package/live acceptance is claimed; installed alpha.31 is unchanged. | Documented — QSO editing and DXCC/QSL workflows; comparable field-provenance findings were not established. | Documented — log management and service reconciliation; comparable field-provenance findings were not established.
ADIF field preservation | Source complete for nine reviewed compatibility stages — local records retain a JSON field bag; unknown/custom fields, Unicode, station/contact and RX/TX data survive supported ADI/ADX round trips. UTF-8 byte scanning, FT4/FT2/JTTY MFSK-submode export, C4FM/DSTAR DIGITALVOICE-submode handling and import-only PSK31/PSK63/PSK63F/PSK125/PSKAM10 to PSK/submode normalization are fixed. Latest Swift 18/18 and frontend 1,202/1,202 and TypeScript pass at PSKAM10 (770dda2). Remaining 3.1.8 audit and package/real-log acceptance stay open; ADIF_VER stays 3.1.7. | Documented — import/export plus four user-definable logging fields. | Documented — ADIF-oriented logbook and online-service interchange; unknown-field preservation was not established in the reviewed README.
ADIF import — duplicate/update review | Source complete — bounded ADI/ADX preview, invalid-record reporting, explicit insert/duplicate counts and revision-fenced field update choices. | Documented — ADIF import and exchange with other logging tools. | Documented — import and service reconciliation are present; exact duplicate/update review behavior was not established in the reviewed README.
ADIF export — all, filtered and selected | Source complete — freezes a consistent all/filtered/selected snapshot before paged ADI or ADX export. | Documented — quick/detailed queries and export routines. | Documented — log and service integrations imply interchange; exact selected/filtered export behavior was not established in the reviewed README.
Logbook table — selectable columns | Source complete — normal Logbook columns are available in dedicated, detached and map-split views with separate visibility preferences. | Documented / locally observed — configurable Logbook columns and table sizing. | Documented — customizable GUI and saved table state patterns.
Logbook table — adjustable column widths | Source complete — bounded pointer, keyboard and numeric width controls persist per presentation context; packaged follow-up acceptance remains open. | Documented / locally observed — adjustable table columns. | Documented — movable/visible columns are used in QLog tables; exact persistence varies by view.
Previous QSOs — independent window | Source and synthetic visual stage complete — a native Window-menu surface follows the canonical Log QSO draft and existing local-history projection, closes on Canvas transition, and adds no contact owner. Focused frontend/Rust/build checks and 320/420/900-pixel visual checks pass; exact packaged native acceptance remains. | Documented — QSO search and entity/QSO search windows. | Not established in reviewed evidence as a dedicated independent window.
Callsign and DXCC intelligence | Source complete — dedicated/detached panel with QRZ enrichment, date-aware CTY/DXCC classification, grids, zones, distance and worked/confirmed matrices. The incorrect all-PJ-to-305 shortcut is removed, stored DXCC overrides remain authoritative, and a bounded read-only Logbook preview explains inferred PJ changes without a correction route. Exact-package/copied-log acceptance remains open. | Documented — QRZ/HamQTH lookups, Club Log DXCC recognition and detailed DXCC status. | Documented — QRZ.com and HamQTH callbook integration plus club-member lookup.
Operating goals and opportunity context | Passive source window complete — explicit callsign, entity/band/mode and IOTA/POTA/SOTA/WWFF targets are evaluated against station-scoped retained history and official opportunities. The native window keeps selection ephemeral and separates worked, confirmed, sponsor evidence and sponsor credit while showing source age/time basis. Cluster observations are explicitly excluded; package acceptance and opt-in reminders remain open. | Documented — DX-alarm, band-map and award-status workflows; the reviewed evidence did not establish the same shared goal model. | Documented — alerts, custom filters and award tracking; the reviewed evidence did not establish the same shared goal model.
Connection Doctor and support preview | Passive native window plus click-only redacted export source complete — fixed provider/configuration/connection/freshness/capability stages consume only already-retained allowlisted state. The typed preview and exported JSON cannot represent secrets, endpoints, identifiers, raw errors, radio values, timestamps or log contents. The former late-CSS bundle gate is fixed; exact-package Save/Cancel/overwrite and retained-provider acceptance remain open. | Not established as a comparable product surface in reviewed primary evidence. | Not established as a comparable product surface in reviewed primary evidence.
Wavelog two-way reconciliation | Installed / live accepted — read-first reconciliation imported safe contacts and refreshed linked confirmations/enrichment without deleting or overwriting ambiguous records. | Not documented as a native Wavelog workflow in reviewed primary evidence. | Documented — Cloudlog/Wavelog integration.
Confirmation refresh from remote services | Installed / live accepted through Wavelog — LoTW, eQSL, QRZ and enrichment changes update matching local QSOs while ambiguous identities remain held for review. | Documented — direct LoTW/eQSL workflows and Club Log real-time synchronization. | Documented — LoTW, eQSL, QRZ.com, Club Log, HRDLog.net and Cloudlog/Wavelog integrations.
QRZ.com callbook lookup | Partial — Keychain-backed live lookup, operator-edit preservation and precise-grid targeting exist; cache/session/privacy controls remain. | Documented — QRZ.com and other online directory queries. | Documented — QRZ.com callbook integration.
QRZ.com log upload | Source complete — prospective default-off upload owner with vault credentials, exact claims, durable receipts and no ambiguous replay; live account acceptance open. | Documented via the separate real-time upload utility. | Documented — QRZ.com online-log integration.
Club Log upload/sync | Source complete for prospective upload; installed Wavelog reconciliation also receives Club Log-related log state. Direct live account acceptance remains open. | Documented — real-time Club Log synchronization. | Documented — Club Log integration.
Online-log follow-up evidence | Source and browser verified — generation-fenced local route and Logbook row panel expose canonical QRZ/Club Log delivery state, receipt revision and attempt age, separately from retained paper/LoTW/eQSL confirmations. Opening performs no fetch; explicit Refresh reads local evidence, and Close/context changes retire pending reads. Swift route 1/1, Rust permission 1/1, frontend 31/31, TypeScript/build/bundle gates and 640x480/1280x800 actual-Logbook browser checks pass. Provider acceptance/match age and sponsor credit remain unknown; exact-package/native and live-account acceptance remain open. | Documented service status and confirmation workflows; exact evidence boundaries were not audited. | Documented online-log integrations; exact evidence boundaries were not audited.
HRDLog.net upload | Outstanding — deferred until the current official service contract is verified and implemented behind the same vault/receipt/no-replay boundary. | Documented via the separate real-time upload utility. | Documented — HRDLog.net integration.
Direct LoTW and eQSL workflows | Outstanding as independent providers — confirmation fields and Wavelog refresh are supported, but direct credential/upload/download owners remain separate programmes. | Documented — direct upload/download, QSL statistics and paper-QSL workflows. | Documented — LoTW and eQSL integration; TQSL is optional for LoTW and eQSL can download QSL pictures.
WSJT-X Logged ADIF UDP intake | Source complete — explicit default-off receive-only listener for official Logged ADIF messages; loopback/multicast validation and duplicate-safe local save; live WSJT-X acceptance open. | Documented / locally inventoried — configurable WSJT-X UDP logging and save choices. | Documented — WSJT-X integration; source audit shows one configurable unicast/multicast receiver and QSO Logged/Logged ADIF parsing.
WSJT-X CQ activity and novelty | Source complete — bounded receive-only FT8/FT4 CQ activity feeds named alerts with current local call/DXCC novelty; no reply, CAT, PTT or save authority. | Documented / locally inventoried — WSJT-X activity-window and callsign-checking choices. | Documented — WSJT-X activity can feed its alert evaluator.
DX Cluster | Implemented — native shared cluster owner, profiles, filters, console paths and retained spot state; configuration and display remain separated. | Documented — internet/local-skimmer cluster, terminal and separated/alerted spots. | Documented — DX cluster integration.
Spot History | Source complete — separate retained local reports, search/filter/statistics and read-only review. Detached column controls exist; packaged/live retention acceptance remains open. | Documented — incoming cluster data and spot/search workflows; exact retained-history model differs. | Documented alert/history tables; exact long-term raw report retention was not established in the reviewed README.
Named DX/WSJT-X alert rules | Source complete — independently enabled structured rules, all matching names, bounded dedup/rate limiting and passive recent-alert dashboard. Each retained event explains its call/DXCC/band/mode/special evidence and first-to-last report history; compact windows use cards instead of horizontal scrolling. | Documented — DXCC/band/mode/IOTA novelty, confirmation source choices, wildcard station watches and optional spoken delivery. | Documented — named cloneable rules combining source, callsign, entity, novelty, geography, comment, band, mode, memberships and activity references.
Alert delivery without RF authority | Source complete — native default-off popup plus optional sound, no action button or station authority; installed live-cluster popup/sound acceptance open. | Documented — color-only or opt-in spoken alarm delivery. | Documented — optional bell and outbound UDP; QLog may also tune/reply from alert UI, which OM0RX-xLog intentionally does not copy.
World map and grayline | Implemented — online hybrid/satellite/standard map, spot and DXCC layers, route/grayline/sun overlays and semantic labels; prolonged operator observation remains. | Documented — maps/grayline and DXCC/spot workflows. | Documented — online and offline map.
Band maps | Implemented — multiple independently keyed band maps, follow-radio behavior and detached windows; final mixed-size/multi-display packaged acceptance remains. | Documented / locally observed — multiple independent band-map windows. | Documented — bandmap.
Canvas and separate-window modes | Source complete — persistent Canvas/Separate Windows choice, named native task windows and geometry recovery. Switching to Canvas closes child windows; simultaneous multi-display packaged acceptance remains. | Documented / locally observed — many named native windows with saved placement conventions. | Documented — customizable GUI and saved layout profiles; macOS is experimental.
Responsive detached windows | Partial — common chrome removal and targeted fixes cover many roles. Detached Propagation rows align; Station Status and Rotor use the shared inset; Rotor starts at the top. Focused 31/31 UI, rendered geometry, Band Map 380×1100, Callsign Intelligence 680×500 and Rotor 676×500/400×600 browser checks pass without page overflow. The packaged all-window resolution/scale matrix remains outstanding. | Mature native macOS window behavior is the reference; exact responsive tests were not obtained. | Recommended resolution is 1920×1080; cross-platform GUI is customizable, but compact-window behavior was not established.
Custom canvas panel move/resize | Source complete for traditional unlock/edit interaction — panel arrow enters edit mode, title drags position and edges/corners resize; broader mixed-size acceptance remains. | Not a directly comparable canvas workflow in reviewed evidence. | Documented saved layout profiles; exact freeform canvas resize interaction differs.
Radio control providers | Implemented — Remote Agent, direct FLEX LAN and local Hamlib paths are capability-separated with explicit selection/connect and retained observed state. | Documented — Kenwood, Elecraft, Yaesu and Icom support, with deeper controls for selected models. | Documented — Hamlib, OmniRig, TCI and FLRig.
TCI rig control — SunSDR/ExpertSDR and compatible servers | Source complete through receive tune/filter, configured-TRX split, global TX-frequency telemetry, APP_FOCUS, addressed RX_CLICKED_ON_SPOT, legacy CLICKED_ON_SPOT and receipt-only CW_MACROS_EMPTY and opaque CALLSIGN_SEND and per-address VFO_LOCK plus RX_CHANNEL_SENSORS and separate deprecated RX_SENSORS plus formal-five-field TX_SENSORS token observations. Passive notifications retain independent producer receipts; legacy clicks infer no TRX/channel/VFO. CW_MACROS_EMPTY proves no queue-empty, TX/RX, CW or RF authority. APP_FOCUS Swift 45/45, legacy-click 50/50 (lifecycle rerun) CW receipt 55/55 and CALLSIGN_SEND 60/60 (34 protocol + 26 session) pass. CALLSIGN_SEND uses strict validation/reconnect clearing and confers no target/contact identity authority, command correlation, TX completion/success or RF inference. VFO_LOCK 66/66 (38 protocol + 28 session) retains independent exact-address producer times, validates exactly three arguments within application/discovery bounds, prunes on discovery shrink and clears on reconnect. It grants no owner/expiry, tune confirmation, configured freshness or control authority. RX_CHANNEL_SENSORS preserves exact bounded ASCII decimals per address without Double conversion or physical range/calibration/quality/readiness/freshness/control claims; discovery prunes and reconnect clears. Six new tests pass twice, protocol 42/42; broader session rerun at ed8ed37 was 71/72 on unchanged testDroppingLastSessionReferenceClosesPendingConnection (closeCount 0 vs 1); initial existing tune-yield miss passed rerun. Build/diff clean. 2d7bb1f adds deprecated server-only RX_SENSORS as separate per-TRX raw bounded decimal tokens plus local producer receipt, never channel-attributed or merged with RX_CHANNEL_SENSORS. TRX discovery prunes, channel-count changes do not remap and reconnect clears. No physical range/calibration/readiness/freshness/control/RF inference. Later independent focused tests 78/78 pass; earlier timing miss is not claimed fixed. dbf6e36 adds passive formal-five-field TX_SENSORS raw per-TRX receipts (84/84); malformed printed example rejects and no TX/RF/physical power/SWR authority is inferred. Explicit controls retain the existing no-replay/readback owner. Transmit/PTT, split/TX-VFO controls, outbound spots, audio/IQ and package/live-server/RF acceptance remain open. 711d4c4 retains global MUTE from pinned TCI pp 21–22 with own receipt, strict bool and reconnect clear; no encoder/query/setter/control/configured readiness/tune/TX/RF effect. New 5/5 and protocol 53/53 pass; broad 88/89 retains unchanged lifecycle closeCount 0 vs 1. Root combined-tree new 5/5 passes after R10 test compile fixes, not a lifecycle fix. 46c862b separately observes RX_MUTE for exact receiver/strict bool, with independent receipts, pruning/reconnect clearing and no configured freshness/readiness/tune/TX/control/RF authority. Agent 95/95 and root new 6/6 pass. Earlier lifecycle flake and package/live gates stay disclosed. | Not established in the reviewed primary RUMlogNG evidence. | Documented — QLog supports all TCI-compatible rigs through its native TCI provider.
Safe simplex tuning and Tune/Cancel | Source complete — durable exact-owner transactions, one existing-worker dispatch, no replay and authoritative readback where available; packaged/hardware acceptance open. | Documented — CAT can set transceiver parameters from the logbook and vice versa; safety contract was not audited. | Documented — rig control and cluster/bandmap integration; safety contract was not audited.
Amplifier Operate/Standby | Source complete — one shared Agent-only durable owner provides separate Operate and urgent Standby lanes, exact identity/freshness fences, one-attempt journal-before-send dispatch and explicit unknown-receipt recovery. Packaged Agent, amplifier-readback, hardware and RF acceptance remain. | Model/device controls exist for supported station equipment; exact KPA-style workflow was not established. | No comparable amplifier owner was established in reviewed evidence.
Rotor control | Source complete — shared manual Goto, native urgent Stop and standalone Auto/Stop with exact owner/generation fences; packaged/hardware acceptance open. | Documented through a companion advanced Rotor application interacting with RUMlogNG and WSJT-X. | Documented — Hamlib and PSTRotator control.
CW keyer and console | Implemented foundation — shared saved macros/new-QSO context plus explicit selected-radio and independent WinKeyer ownership; remaining end-to-end hardware acceptance is open. | Documented — K1EL WinKeyer, CW keyer and RTTY application. | Documented — CWDaemon, FLDigi, Morse over CAT, WinKey v1/v2 and CW Console.
Propagation display | Source complete with live provider proof — bounded HamQSL/N0NBH refresh and correct freshness semantics; final packaged outage/freshness observation remains. | Not highlighted in reviewed primary feature listing. | Not highlighted in reviewed primary feature listing.
Awards and statistics | Implemented foundation — nine native calculators plus a 192-programme research library. 6d9b186 adds pure QRPDXCCPreflightV1 snapshot screening (7/7 Swift) as an R09 dependency only: candidates/exclusions/unknowns and exact retained-power checks. Candidate stored DXCCs are not validated entities, progress, completion or sponsor credit. Measurement, sponsor validity, applicant scope, land/direct-contact eligibility and declaration remain unresolved; executable sponsor rules, application/export, route/UI and package/live acceptance stay open. | Documented — DXCC plus IOTA, CQ/ITU zones, grids, states, counties, DOKs and detailed QSL statistics. | Documented — basic awards and station statistics.
Contest logging | Outstanding as a separate programme — ordinary logging remains primary; do not add empty parity UI. | Documented — specialized contest/DXpedition logger with scoring and ESM. | Documented — basic contest support; QLog states contests are not its current focus.
Paper QSL and label printing | Outstanding as a dedicated workflow; ADIF QSL fields are preserved and remote confirmations can refresh. | Documented — incoming paper QSL management and QSL label printing. | No paper-label workflow established in the reviewed README.
Station/location profiles | Partial — saved station identity/equipment/workspace configuration exists with separate radio, rotor, antenna and activity ownership; profile UX can be improved without unsafe implicit apply. | Documented / locally observed — operator identity, radios, QRGs, modes/satellites, cluster, QSL and service groups. | Documented — station location profile support.
Secure credential storage | Implemented — Keychain/vault-backed provider credentials with ownership and revision fencing. | Uses macOS platform storage for supported services; exact architecture was not audited. | Documented — system keyring/credential store support on Linux, Windows and macOS.
Backups | Partial — local backup/restore safety exists; optional remote FTP/FTPS/SFTP work is active in a separate user-owned change set and is not counted complete here. | Not established in reviewed primary feature listing. | Not established in reviewed primary feature listing.
Cross-platform delivery | Partial — one shared UI/domain targets macOS, Windows and Linux; Mac is the current acceptance focus and Windows/Linux packaging is intentionally deferred. | Mac only. | Linux and Windows supported; macOS is documented as experimental/developer-only.
Privacy and telemetry | Implemented by design — local-first operation, explicit external-service enrollment and no hidden station/network actions in source acceptance tests. | Current App Store disclosure says data is not collected. | Documented — no ads, user tracking or hidden telemetry.

## Outstanding
Outstanding work and decisions
Priority reflects safety and workflow dependency, not implementation effort. Acceptance evidence is stated separately so source-complete work is not mistaken for installed or live proof.
Priority | Feature or decision | Current status | Outstanding work | Evidence required | Reference or inspiration
P0 | Amplifier Operate/Standby owner | Source complete | Run exact-source packaged Agent acceptance without RF transmission; then obtain authoritative amplifier/drive readback and hardware acceptance under operator control. | Exact-source Mac package, controlled Agent proof, amplifier/hardware evidence | OM0RX safety model; QLog does not provide a comparable contract
P0 | PTT owner | Source complete | Run exact-source packaged and controlled live Agent/FLEX acceptance, including release timing and prior-app fail-closed recovery without RF transmission. | Exact-source Mac package, live observed-state and physical release evidence | OM0RX stronger least-authority design
P0 | All-window responsive acceptance | Partial | Exercise every detached window at compact, normal, large and mixed-display scales; fix clipping and unused space. | Packaged macOS screenshots and interaction checks | RUMlogNG native-window maturity
P0 | Separate Windows to Canvas transition | Source complete | Confirm switching modes closes all child windows and restores Canvas without stale ownership or geometry. | Packaged simultaneous-window acceptance | RUMlogNG Window discoverability; QLog saved profiles
P0 | Logbook arbitrary ADIF editing | Source complete | Run packaged macOS pointer/keyboard interaction and legacy-log round-trip acceptance; retain explicit review for malformed legacy optional values. | Packaged UI review and copied-database round-trip evidence | RUMlogNG edit/search/export workflow
P0 | ADIF 3.1.8 conformance | Nine compatibility stages complete | Complete the remaining enum/deprecation and MODE/SUBMODE audit before changing ADIF_VER; run copied-log/package and service-specific interoperability acceptance. | Pinned official fixtures, copied-log round trip and exact package | Official ADIF 3.1.8
P0 | PJ/DXCC affected-record review | Read-only source preview complete | Run the bounded preview against a disposable copied real logbook; preserve explicit DXCC/manual overrides and require separate approval before any reversible correction feature. | Copied real-log preview, exact-package UX and rollback evidence | Official/date-qualified CTY rules
P1 | Full TCI radio provider | Receive tune/filter plus passive split, TX-frequency, APP_FOCUS, addressed/legacy spot-click CW_MACROS_EMPTY receipt and opaque CALLSIGN_SEND plus VFO_LOCK, RX_CHANNEL_SENSORS and separate deprecated RX_SENSORS plus formal-five-field TX_SENSORS tokens source complete; latest focused tests 84/84; passive global MUTE source complete (broad gate88/89, new 5/5 root rerun); exact-receiver RX_MUTE source complete (agent 95/95, root new 6/6) | Extend the existing no-replay owner with separately reviewed split/TX-VFO controls, urgent release and optional audio/IQ slices; passive notifications never become configured evidence/inventory or CW/RF authority. Transmit/PTT keeps its own explicit authority. | Simulated-server races, package tests, then operator-controlled SunSDR acceptance | Official ExpertSDR3 TCI specification and QLog behavior
P1 | Previous QSOs window | Source plus synthetic visual complete | Run exact packaged native-window, focus/keyboard and Canvas-transition acceptance; retain the canonical draft/history owners. | Exact-source macOS package and mixed-window acceptance | RUMlogNG entity/QSO search surfaces
P1 | Direct LoTW/eQSL | Outstanding | Design separate vault, receipt, reconciliation and no-replay owners; do not piggyback on Wavelog credentials. | Provider sandbox/live-account acceptance | RUMlogNG and QLog service workflows
P1 | HRDLog.net | Outstanding | Verify the current official contract, then add a default-off prospective uploader if the contract is safe and useful. | Official API evidence and live-account acceptance | QLog and RUMlog upload utility
P1 | WSJT-X live acceptance | Source complete | Run the default-off Logged ADIF and CQ listeners against a real WSJT-X instance without reply/CAT/PTT authority. | Live UDP capture and duplicate/no-replay evidence | QLog and RUMlogNG UDP workflows
P1 | Alerts live acceptance | Source complete | Verify popup, optional sound, expiry, clear and suppression counters from real retained cluster/WSJT-X traffic. | Installed live-cluster evidence | QLog rule table and RUMlogNG novelty alarms
P1 | Saved QSO filter profiles | Source complete | Package-test Save/Apply/Clone/Rename/Delete against the canonical query and verify keyboard/focus behavior across window contexts. | Exact-source package, UX and persistence acceptance | QLog custom filters and layout profiles
P1 | Connection Doctor surface | Native window and redacted export source complete | Verify native Save/Cancel/overwrite in the exact package and real retained-provider states; preserve the closed allowlist and no-action boundary. | Privacy review, exact-package and retained-provider acceptance | OM0RX least-data diagnostic design
P1 | Operating-goal UI | Passive native source window complete | Package-test the explained retained-source window; consider explicit opt-in timezone reminders as a separate slice. | Exact-package presentation/freshness and optional reminder tests | RUMlogNG alarms/award status; QLog alerts/filters
P1 | Online-log follow-up UI | Read-only route/UI source and browser verified | Accept the exact package/native interaction; define provider acceptance/match timestamps and sponsor rules before extending the retained-evidence contract. Upload delivery never establishes confirmation or sponsor credit. | Exact-package/native interaction and live-account evidence | RUMlogNG/QLog online-log status workflows
P1 | Contest logging | Programme decision | Decide whether to build a separate contest engine with scoring, exchange, ESM and Cabrillo/REG1TEST export. | Rules, performance and contest-specific acceptance plan | RUMlogNG mature contest workflow; QLog basic contests
P2 | Paper QSL and labels | Programme decision | Decide whether paper-QSL tracking and label printing belongs in the product or remains an external workflow. | Printer/template requirements and operator demand | RUMlogNG
P2 | Regional band/allocation guides | Candidate | Add only from authoritative regional data with operator-selected region and update provenance. | Authoritative data source and boundary tests | QLog band guides; RUMlogNG editable QRG segments
P2 | Windows and Linux packages | Deferred | Build only after Mac visual and workflow acceptance, then validate platform-specific keyrings, radios and window behavior. | Native Windows/Linux packages and hardware tests | QLog cross-platform distribution

## Enhancement Review
Enhancement review reconciliation
The supplied 24-item review is reconciled against current source. States distinguish implemented source, unaccepted gates, useful extensions, new candidates and deliberate deferrals.
ID | Priority | Reconciled state | Existing reuse point | Next accepted outcome
R01 | P0 | Resolver and read-only preview source complete; package/data-impact review open | CTYResolver, stored QSO DXCC override and bounded Logbook preview | Accept against a disposable copied log; never bulk rewrite.
R02 | P0 | Implemented; package/hardware acceptance open | Durable Tune, Cancel, PTT, amplifier and rotor owners | Exact-package stale/unknown/release checks, then authorized hardware/RF.
R03 | P0 | Source complete; copied-log acceptance open | ADIF field bag, contact mutation, delete/undo | Edit/undo/conflict plus ADI/ADX round-trip proof.
R04 | P0 | Nine compatibility stages complete | ADIF parser/writer and frontend transfer | Finish remaining 3.1.8 audit after PSK63/PSK63F/PSK125/PSKAM10; retain ADIF_VER 3.1.7.
R05 | P0 | Detached geometry and targeted browser checks complete; package acceptance open | Native window geometry and Canvas/Separate Windows owner | Package-test all sizes, displays, DPI, focus, keyboard and accessibility.
R06 | P1 | Passive model, worker and native UI complete; package open | Opportunity feeds, spots, alerts, awards and history | Package-test 52010e3; retain explicit cluster-provenance exclusion.
R07 | P1 | Read-only route/UI source and browser verified; package/provider open | Sync/delivery/confirmation and award state | Package-test 5486aff; retain unknown provider ages/credit until timestamp and sponsor-rule contracts exist.
R08 | P1 | Existing service programme | Vault plus durable claim/receipt patterns | Direct LoTW/TQSL station/certificate/upload/download owner.
R09 | P1 | QRP DXCC preflight dependency source complete; executable award open | Award calculators, research registry and QRPDXCCPreflightV1 | 7/7 Swift screens candidates only; resolve measurement/sponsor/scope/eligibility/declaration requirements before executable rules, application/export or credit.
R10 | P1 | Read-only core/route/Details UI source complete; acceptance/corrections open | QSODataQuality, exact-contact canonical route and Logbook Details | c4b1602: root 35/35 + detached 6/6; agent build/tsc/browser geometry pass. Next native/package/copied-log/live/full coverage; no correction, provider refresh or award/sync delta.
R11 | P1 | New candidate | Import preview, semantic identity and workspace snapshots | Isolated migration trial, delta report, exceptions and rollback.
R12 | P1 | Useful extension; baseline exists | Existing split/VFO UI and CAT owners | Explicit split intent, dual readback and safe simplex return.
R13 | P1 | New candidate | Canonical draft and spot/opportunity admission | Local scratch queue; explicit promotion only.
R14 | P1 | Useful extension | Station identity, activation directories and QSO ADIF | Immutable activation session and explicit return home.
R15 | P1 | Previous QSOs and saved-filter source complete; package open | Logbook query snapshot and canonical detached history context | Package-test native history plus cloneable canonical filters.
R16 | P1 | Native window and click-only redacted export source complete; package open | Retained station diagnostics only | Package-test Save/Cancel/overwrite and real retained states; preserve the closed allowlist.
R17 | P1 | Existing acceptance; partial | 100k proof, capacity guard, backups and recovery owners | 1m, contention, kill/restart, outage and isolated restore.
R18 | P2 | Optional extension | Spot history plus antenna/power metadata | Passive self-call RBN analysis with comparability limits.
R19 | P2 | New candidate; deferred | CW/PTT safety patterns | Default-off local voice/audio only after PTT acceptance.
R20 | P2 | Passive shared model/route/UI complete; reminders open | Existing 425DXN and activation feeds | Use existing scheduled evidence for explicit opt-in timezone reminders only.
R21 | P2 | New candidate | QSO notes, history and confirmation fields | Private journal/attachments excluded from sync/export by default.
R22 | P2 | Useful data/editor extension | Satellite ADIF/Wavelog mapping and arbitrary fields | Optional validated satellite/VHF editor; defer orbit/Doppler.
R23 | P2 | Deferred product decision | Ordinary logger only | Choose casual export versus real contest programme.
R24 | P2 | Deferred by Mac-first boundary | Shared architecture | Exact Windows/Linux packages only after Mac acceptance.

## Sources
Sources and comparison limits
Feature statements are conservative. 'Not established' means the reviewed primary evidence did not prove the feature; it does not prove absence. Third-party products are references only and no code or data was copied.
Product | Source or evidence | Verified | Scope and limits
OM0RX-xLog | Current implementation checkpoint c4b160281b6fbf1a65adcb8f782ec41503a0f969 | 2026-10-16 | PROJECT_STATUS.md, PROJECT_BOARD.md, operator-feedback tracker and enhancement-recommendations reconciliation. Source/test/browser results remain separate from package/native/live/hardware acceptance; installed alpha.31 is unchanged.
OM0RX-xLog | https://github.com/oliverbross/OM0RX-xLog/commit/c4b160281b6fbf1a65adcb8f782ec41503a0f969 | 2026-10-16 | Latest separate stages: passive exact-receiver RX_MUTE (46c862b; agent 95/95, root new 6/6), PSKAM10 ADIF normalization (770dda2; Swift 18/18, frontend 1202/1202, tsc; ADIF_VER 3.1.7), and exact-contact Logbook Details findings UI (c4b1602; root 35/35 + detached 6/6, agent build/tsc/browser geometry). Installed alpha.31 unchanged; earlier lifecycle flake remains disclosed. Native/package/live, full audits and correction/provider-refresh gates remain open.
Enhancement review | OM0RX-xLog_Codex_Enhancement_Review_2026-10-16.md and OM0RX-xLog_Enhancement_Backlog_2026-10-16.xlsx | 2026-10-16 | User-supplied advisory sources reconciled against the active checkout; recommendations are classified on the Enhancement Review sheet.
RUMlogNG | Installed RUMlogNG 6.5.1, build 727 | 2026-10-16 | Read-only bundle metadata. Prior local audits inspected menus, bundled help and visible Settings labels without reading user data or changing preferences.
RUMlogNG | https://apps.apple.com/us/app/rumlogng/id964454561?mt=12 | 2026-10-16 | Current official App Store description: logging, QSL, contest, cluster, CAT, WinKeyer, awards and Club Log features; macOS 12.4+ and Mac-only.
RUMlogNG | https://dl2rum.de/forum/app.php/downloads | 2026-10-16 | Official developer download page and companion utilities, including the real-time upload utility and Rotor application.
RUMlogNG | https://dl2rum.de/RUMlogNG/docs/en/pages/DX-Alarm-Setting.html | 2026-10-16 | Official DX Alarm behavior used as alert explainability inspiration; no implementation code was copied.
RUMlogNG | https://dl2rum.de/RUMlogNG/docs/en/pages/Win-DX-Spots.html | 2026-10-16 | Official DX Spot window documentation used for behavior comparison only.
QLog | https://github.com/foldynl/QLog/blob/master/README.md | 2026-10-16 | Official feature inventory for GUI, radio/rotor/CW, callbooks, DX cluster, online logs, maps, WSJT-X, awards, contests and supported operating systems.
QLog | https://github.com/foldynl/QLog/commit/cbb75f2f2555a4a84c9761e38075754f4821c27c | 2026-10-16 | Verified upstream HEAD used by the read-only source/workflow audit.
TCI protocol | https://github.com/ExpertSDR3/TCI/tree/b081213ff97150fd29f669c633f060f93c81a286 | 2026-10-16 | Pinned official ExpertSDR3 MIT protocol source for the original codec/reducer implementation; no QLog implementation code was copied.
Comparison method | RUMLOG_WORKFLOW_GAP_AUDIT_2026-10-14.md and QLOG_WORKFLOW_GAP_AUDIT_2026-10-15.md | 2026-10-16 | Behavioral inspiration only. No third-party source, artwork, settings, credentials or logbook data is copied into OM0RX-xLog.